Minutes of the Meeting of the Strategic Planning Committee

of Saddleworth Parish Council Held at the Civic Hall, Lee Street, Uppermill on

Friday 29th July 2016

There were present:	Cllr:	B. Beeley - Chairman

Cllr:	R. Knotts

- Apologies for absence

Apologies were received from Cllrs P. Lord, J. McCann and P. Klonowski.

2.	Update on Neighbourhood Plan

The notes from the meeting held with Elizabeth Dryden-Stuart and Georgina Brownridge on Thursday 30th June formed the agenda for the meeting:

- The OMBC report to seek delegated approval to consult on the designated neighbourhood area was expected to be signed off after 8th July. Once approved, the 6 week consultation period can start. It had been agreed at the meeting on 30th June that the consultation would start in mid August so that the school holidays did not interfere with the process. Email confirmation form Georgina Brownridge to say that the report was approved on 26th July and that consultation will start on 19th August.

- OMBC will collate the consultation responses and draw up the final report. If everything is approved, the plan can be started mid to late November.

- The consultation needs to be advertised throughout the parish. The Communications Committee need to make sure it goes into the Saddleworth Independent, Saddleworth Monthly, Saddleworth and Lees Monthly and InSaddleworth. Emailed Saddleworth Independent 2nd August to ask for a half page “feature” in the September issue.

- Cllr Knotts said he would raise it at the next District Partnership meeting.

- The Clerk will email the community association chairs to get it on to the agendas for their next meetings.

- As Geoff Willerton is currently providing planning advice, he is to be asked whether he could assist with the project either alone or in conjunction with consultants. Grant funding is available until 2018. The planning will start form early October. An application for funding will be submitted but, as the funds have to be spent within 6 months of receipt of the grant the application will be done once the area for the plan had been formally approved.

3.	Date of next meeting

To be arranged